## Sheet1
| Tasks | Days
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
initiating | bar: Days 1 to Days 2
Assign Project Manager | bar: Days 1
Assign other team members | bar: Days 1
Initial meeting with Client | bar: Days 2
Analysis Tasks | bar: Days 3 to Days 6
Create scope plan | bar: Days 3
Create WBS and Gantt chart | bar: Days 3 to Days 4
Create activity definitions | bar: Days 3 to Days 4
Create Use Case Definitions and diagram | bar: Days 4 to Days 5
Obtain approval from the Client | bar: Days 6
Design Tasks | bar: Days 5 to Days 14
Define system vision | bar: Days 5 to Days 8
Define Requirements | bar: Days 5 to Days 8
Define system Components | bar: Days 5 to Days 8
Define User Interface Design | bar: Days 5 to Days 8
System Vision, Requirement and components | bar: Days 5 to Days 8
Create Class Diagram | bar: Days 5 to Days 8
initiate user interface design and create Wireframes and | bar: Days 5 to Days 8
create prototype | bar: Days 9 to Days 10
Test user interface prototype | bar: Days 10 to Days 11
Define user interface | bar: Days 12
Team meeting to conclude design tasks | bar: Days 13
Meet with client for design approval | bar: Days 13 to Days 14
Build Tasks | bar: Days 7 to Days 24
Initialise Git and Github Repository | bar: Days 7
Develop backend program code | bar: Days 7 to Days 19
Develope frontend program code | bar: Days 7 to Days 22
Test Code Backend | bar: Days 7 to Days 19
Recitfy any issues from backend test | bar: Days 7 to Days 22
Test Code Frontend | bar: Days 7 to Days 22
Rectify any issues from front end test | bar: Days 7 to Days 24
Test Tasks | bar: Days 10 to Days 24
Test user experience | bar: Days 10 to Days 24
Conduct user acceptance test | bar: Days 25 to Days 26
Record test findings | bar: Days 25 to Days 26
Attend approval from the client for rollout | bar: Days 27 to Days 28
Controlling
Status reports
Update plans
Closing | bar: Days 29 to Days 30
Lessons learned | bar: Days 29 to Days 30
prepare final report | bar: Days 29 to Days 30
Conduct project review in a team meeting | bar: Days 30
Assign Project Manager
|  |  |  | Start: |  | ID:
|  |  |  | Finish: |  | Dur:
Tasks
ID |  | Days 1: Duration; Days 2: Resource; Days 3: Predecessor
1 | initiating
1.1 | Assign Project Manager
1.2 | Assign other team members
1.3 | Initial meeting with Client
2 | Analysis Tasks
2.1 | Create scope plan
2.2 | Create WBS and Gantt chart
2.3 | Create activity definitions
2.4 | Create Use Case Definitions and diagram
2.5 | Obtain approval from the Client
3 | Design Tasks
3.1 | Define system vision
3.2 | Define Requirements
3.3 | Define system Components
3.4 | Define User Interface Design
3.5 | System Vision, Requirement and components
3.6 | Create Class Diagram
3.7 | initiate user interface design and create Wireframes and
3.8 | create prototype
3.9 | Test user interface prototype
3.1 | Define user interface
3.11 | Team meeting to conclude design tasks
3.12 | Meet with client for design approval
4 | Build Tasks
4.1 | Initialise Git and Github Repository
4.2 | Develop backend program code
4.3 | Develope frontend program code
4.4 | Test Code Backend
4.5 | Recitfy any issues from backend test
4.6 | Test Code Frontend
4.7 | Rectify any issues from front end test
5 | Test Tasks
5.1 | Test user experience
5.2 | Conduct user acceptance test
5.3 | Record test findings
5.4 | Attend approval from the client for rollout
6 | Controlling
6.1 | Update Plans
6.2 | Status reports
7 | Closing
7.1 | Lessons learned
7.2 | prepare final report
7.3 | Conduct project review in a team meeting