## VicAccidentStats App (2022-09-0
WBS # | Name / Title | Type | Start Date | End Date | Percent Complete | Resources | Predecessors | Column1 | Comments | Task Color
1 | VicAccidentStats App | project | 2022-08-15 | 2022-09-23 | 31.11
1.1 | Initiating | group | 2022-08-15 | 2022-08-17 | 100
1.1.1 | Assign Project Manager | task | 2022-08-15 | 2022-08-15 | 100 |  |  |  |  | orange1
1.1.2 | Assign other team members | task | 2022-08-16 | 2022-08-16 | 100 | Kiarna Broomhead | 1.1.1 |  |  | orange1
1.1.3 | Initial meeting with Client | task | 2022-08-17 | 2022-08-17 | 100 | Kiarna Broomhead | 1.1.2 |  |  | orange1
1.2 | Analysis | group | 2022-08-18 | 2022-08-22 | 100
1.2.1 | Create scope plan | task | 2022-08-18 | 2022-08-18 | 100 | Taylor Edgerton | 1.1.3 |  |  | purple1
1.2.2 | Create WBS and activity definitions | task | 2022-08-18 | 2022-08-18 | 100 | Davinder Grewal |  |  |  | purple1
1.2.3 | Create Gantt Chart | task | 2022-08-19 | 2022-08-19 | 100 | Davinder Grewal | 1.2.1,1.2.2 |  |  | purple1
1.2.4 | Define and create Use Case diagram | task | 2022-08-19 | 2022-08-19 | 100 | Taylor Edgerton |  |  |  | purple1
1.2.5 | Obtain approval from the Client | task | 2022-08-22 | 2022-08-22 | 100 | Kiarna Broomhead | 1.2.3,1.2.4 |  |  | purple1
1.3 | Design | group | 2022-08-23 | 2022-09-06 | 100
1.3.1 | Define system requirements | task | 2022-08-23 | 2022-08-24 | 100 | Kiarna Broomhead | 1.2.5 |  |  | blue3
1.3.2 | Define system components | task | 2022-08-23 | 2022-08-24 | 100 | Taylor Edgerton |  |  |  | blue3
1.3.3 | Create system vision document | task | 2022-08-25 | 2022-08-26 | 100 | Davinder Grewal | 1.3.1,1.3.2 |  |  | blue3
1.3.4 | Define and Initiate GUI Design | task | 2022-08-29 | 2022-08-30 | 100 | Taylor Edgerton | 1.3.3 |  |  | blue3
1.3.5 | Create Class Diagram | task | 2022-08-29 | 2022-08-30 | 100 | Taylor Edgerton |  |  |  | blue3
1.3.6 | Create wireframes and prototypes | task | 2022-08-31 | 2022-09-01 | 100 | Kiarna Broomhead | 1.3.4,1.3.5 |  |  | blue3
1.3.7 | Test GUI prototypes | task | 2022-09-02 | 2022-09-02 | 100 | Taylor Edgerton | 1.3.6 |  |  | blue3
1.3.8 | Team meeting to conclude design tasks | task | 2022-09-05 | 2022-09-05 | 100 | Taylor Edgerton, Kiarna Broomhead, Davinder Grewal | 1.3.7 |  |  | blue3
1.3.9 | Meet the client for design approval | task | 2022-09-06 | 2022-09-06 | 100 | Kiarna Broomhead | 1.3.8 |  |  | blue3
1.4 | Build Tasks | group | 2022-09-07 | 2022-09-13 | 55.56
1.4.1 | Initiate Git and Github Repository | task | 2022-09-07 | 2022-09-07 | 100 | Taylor Edgerton | 1.3.9 |  |  | green1
1.4.2 | Develop backend program code | task | 2022-09-08 | 2022-09-09 | 100 | Davinder Grewal | 1.4.1 |  |  | green1
1.4.3 | Test backend code | task | 2022-09-12 | 2022-09-12 | 100 | Davinder Grewal | 1.4.2 |  |  | green1
1.4.4 | Recitfy any issues from backend test | task | 2022-09-13 | 2022-09-13 | 100 | Davinder Grewal | 1.4.3 |  |  | green1
1.4.5 | Develop frontend program code | task | 2022-09-08 | 2022-09-09 | 0 | Taylor Edgerton | 1.4.1 |  |  | green1
1.4.6 | Test Code frontend | task | 2022-09-12 | 2022-09-12 | 0 | Taylor Edgerton | 1.4.5 |  |  | green1
1.4.7 | Rectify any issues from front end test | task | 2022-09-13 | 2022-09-13 | 0 | Taylor Edgerton | 1.4.6 |  |  | green1
1.5 | Testing | group | 2022-09-14 | 2022-09-20 | 0
1.5.1 | Test user experience | task | 2022-09-14 | 2022-09-15 | 0 | Kiarna Broomhead | 1.4.7 |  |  | magenta1
1.5.2 | Conduct user acceptance test | task | 2022-09-16 | 2022-09-16 | 0 | Kiarna Broomhead | 1.5.1 |  |  | magenta1
1.5.3 | Record test findings | task | 2022-09-19 | 2022-09-19 | 0 | Kiarna Broomhead | 1.5.2 |  |  | magenta1
1.5.4 | Obtain approval from the client for rollout | task | 2022-09-20 | 2022-09-20 | 0 | Kiarna Broomhead | 1.5.3 |  |  | magenta1
1.6 | Controlling | group | 2022-08-16 | 2022-09-20 | 0
1.6.1 | Status Reports | task | 2022-08-16 | 2022-09-20 | 0 | Taylor Edgerton, Kiarna Broomhead, Davinder Grewal | 1.1.1 |  |  | yellow1
1.6.2 | Update Plans | task | 2022-08-18 | 2022-09-20 | 0 | Kiarna Broomhead |  |  |  | yellow1
1.7 | Closing | group | 2022-09-21 | 2022-09-23 | 0
1.7.1 | Lessons learned | task | 2022-09-21 | 2022-09-21 | 0 | Kiarna Broomhead | 1.5.4,1.6.1,1.6.2 |  |  | blue1
1.7.2 | Prepare final report | task | 2022-09-22 | 2022-09-22 | 0 | Kiarna Broomhead | 1.7.1 |  |  | blue1
1.7.3 | Conduct project review in a team meeting | task | 2022-09-23 | 2022-09-23 | 0 | Taylor Edgerton, Kiarna Broomhead, Davinder Grewal | 1.7.2 |  |  | blue1